## Received
Date | Material | Units | Quantity | Rate | Material Cost | Admin cost | Total cost | Admin cost Purpose
| Marine Board | Pcs | 5 | 3200 | 16000 |  | 16000 | 1800
| Hoop Iron | Rolls | 2 | 3300 | 6600 |  | 6600
| 4" Nails | Kg | 1 | 180 | 180 |  | 180
| 3" Nails | Kg | 0.5 | 180 | 90 |  | 90
| Roofing Nails | Kg |  | 200 | 0 |  | 0
25/2/2025 | 9" Machine cut stones | Pcs | 12 | 50 | 600 |  | 600
| Natural Stone | Lf | 30 | 60 | 1800 |  | 1800
| Cement | Bags |  | 780 | 0 |  | 0
| Roofing Sheets(10) | Pcs |  | 1680 | 0 |  | 0
| Roofing Sheets(8) | Pcs |  | 1400 | 0 |  | 0
| 3x2 Timber Frames | Lf |  | 65 | 0 |  | 0
| 6x1 Timber Planks | Lf |  | 65 | 0 |  | 0
| 600 x 600 Tiles | Pcs |  | 1200 | 0 |  | 0
| Grout | Kg |  | 350 | 0 |  | 0
| PVC Corner Strips | Pcs |  |  | 0 |  | 0
25/2/2025 | Reflector Jackets | Pcs | 10 | 200 | 2000 |  | 2000
25/2/2025 | Hard hats | Pcs | 10 | 200 | 2000 |  | 2000
| D8 | Pcs | 180 | 620 | 111600 |  | 111600
| D10 | Pcs | 90 | 920 | 82800 |  | 82800
| D12 | Pcs | 100 | 1320 | 132000 |  | 132000
| D16 | Pcs | 100 | 2350 | 235000 |  | 235000
| Binding Wire | Rolls | 3 | 3200 | 9600 |  | 9600
| Hacksaw Blade | Pcs | 10 | 100 | 1000 |  | 1000
25/2/2025 | A3 Safety signage | Pcs | 2 | 3500 | 7000 | 2000 | 9000 | Transport
27/2/2025 | Cement | Bags | 30 | 780 | 23400 | 10000 | 33400 | Material Transport
27/2/2025 | PPR(25mm) | Metres | 300 |  | 0 | 0 | 0 | n/a
18/2/2025 | Ballast | Tons | 10 | 1300 | 13000 | 10000 | 23000 | Material Transport
22/2/2025 | Dust | Tons | 16 | 800 | 12800 | 10000 | 22800 | Material Transport
22/2/2025 | Ballast | Tons | 16 | 1300 | 20800 | 10000 | 30800 | Material Transport
27/2/2025 | Dust | Tons | 16 | 800 | 12800 | 10000 | 22800 | Material Transport
27/2/2025 | Dust | Tons | 16 | 800 | 12800 | 10000 | 22800 | Material Transport
28/2/2025 | Ballast | Tons | 16 | 1300 | 20800 | 10000 | 30800 | Material Transport
2025-12-03 | Ballast | Tons | 16 | 1300 | 20800 | 10000 | 30800 | Material Transport
2025-04-03 | Petrol | Unit | 500 | 1 | 500 | 0 | 500 | n/a
2025-05-03 | Cement | Bags | 20 | 780 | 15600 | 10000 | 25600 | Material Transport
2025-05-03 | Petrol | Unit | 500 | 1 | 500 | 0 | 500 | n/a
2025-05-03 | Diesel | Unit | 500 | 1 | 500 | 0 | 500 | n/a
2025-07-03 | Cement | Bags | 20 | 780 | 15600 | 10000 | 25600 | Material Transport
2025-08-03 | D12 | Pcs | 60 | 1320 | 79200 | 10000 | 89200 | Material Transport
2025-08-03 | D8 | Pcs | 50 | 620 | 31000 | 0 | 31000 | n/a
2025-08-03 | Roofing Sheets(8) | Pcs | 40 | 1400 | 56000 | 0 | 56000 | n/a
2025-08-03 | Binding Wire | Rolls | 3 | 3200 | 9600 | 0 | 9600 | n/a
2025-08-03 | Hoop Iron | Rolls | 4 | 3300 | 13200 | 0 | 13200 | n/a
2025-08-03 | 4" Nails | Kg | 50 | 180 | 9000 | 0 | 9000 | n/a
2025-08-03 | 3" Nails | Kg | 50 | 180 | 9000 | 0 | 9000 | n/a
2025-08-03 | DPC | Rolls | 1 |  | 0 | 0 | 0 | n/a
2025-08-03 | Hacksaw Blade | Pcs | 5 | 100 | 500 | 0 | 500 | n/a
2025-08-03 | Petrol | Unit | 400 | 1 | 400 | 0 | 400 | n/a
2025-11-03 | Cement | Bags | 30 | 780 | 23400 | 10000 | 33400 | Material Transport
2025-11-03 | Grease | Kg | 0.5 | 500 | 250 | 0 | 250 | n/a
2025-11-03 | Diesel | Unit | 650 | 1 | 650 | 0 | 650 | n/a
2025-11-03 | Natural Stone | Lf | 60 | 60 | 3600 | 0 | 3600 | n/a
2025-11-03 | River Sand | Wb | 5 |  | 0 | 0 | 0 | n/a
2025-11-03 | 150mm UPVC Bend | Pcs | 1 | 150 | 150 | 0 | 150 | n/a
2025-11-03 | D16 | Pcs | 35 | 2350 | 82250 | 5000 | 87250 | Material Transport
2025-11-03 | Cement | Bags | 30 | 780 | 23400 | 10000 | 33400 | Material Transport
2025-12-03 | Ballast | Tons | 16 | 1300 | 20800 | 10000 | 30800 | Material Transport
2025-12-03 | Dust | Tons | 15 | 800 | 12000 | 10000 | 22000 | Material Transport
13/3/2025 | Cement | Bags | 25 | 780 | 19500 | 10000 | 29500 | Material Transport
13/3/2025 | Diesel | Unit | 500 | 1 | 500 | 0 | 500 | n/a
14/3/2025 | Ballast | Tons | 16 | 1300 | 20800 | 10000 | 30800 | Material Transport
14/3/2025 | Cement | Bags | 40 | 780 | 31200 | 10000 | 41200 | Material Transport
14/3/2025 | Ballast | Tons | 11 | 1300 | 14300 | 10000 | 24300 | Material Transport
14/3/2025 | Dust | Tons | 6 | 800 | 4800 | 10000 | 14800 | Material Transport
14/3/2025 | First aid box | Pcs | 1 |  | 0 | 5000 | 5000 | Material Transport
14/3/2025 | Diesel | Unit | 600 | 1 | 600 | 0 | 600 | n/a
14/3/2025 | Petrol | Unit | 600 | 1 | 600 | 0 | 600 | n/a
15/3/2025 | Cement (local) | Bags | 20 | 830 | 16600 | 300 | 16900 | Material Transport
17/3/2025 | Cement | Bags | 20 | 780 | 15600 | 10000 | 25600 | Material Transport
17/3/2025 | Dust | Tons | 16 | 800 | 12800 | 10000 | 22800 | Material Transport
17/3/2025 | Waterproofing cement | Kg | 3 |  | 0 | 0 | 0 | n/a
17/3/2025 | Cement (local) | Bags | 5 | 830 | 4150 | 0 | 4150 | n/a
17/3/2025 | Hacksaw Blade | Pcs | 3 | 100 | 300 | 0 | 300 | n/a
18/3/2025 | Natural Stone | Lf | 800 | 60 | 48000 | 10000 | 58000 | Material Transport
18/3/2025 | Grease | kg | 0.5 | 500 | 250 | 0 | 250 | n/a
18/3/2025 | Diesel | Unit | 600 | 1 | 600 | 0 | 600 | n/a
19/3/2025 | Cement (local) | Bags | 5 | 830 | 4150 | 0 | 4150 | n/a
21/3/2025 | Cement | Bags | 30 | 780 | 23400 | 10000 | 33400 | Material Transport
21/3/2025 | BRC | Rolls | 2 |  | 0 | 0 | 0 | n/a
22/3/2025 | Natural Stone | Lf | 800 | 60 | 48000 | 10000 | 58000 | Material Transport
26/3/2025 | Cement | Bags | 40 | 780 | 31200 | 10000 | 41200 | Material Transport
26/3/2025 | Dust | Tons | 16 | 800 | 12800 | 10000 | 22800 | Material Transport
26/3/2025 | Grease | Kg | 0.5 | 500 | 250 | 0 | 250 | n/a
26/3/2025 | Diesel | Unit | 500 | 1 | 500 | 0 | 500 | n/a
25/3/2025 | Petrol | Unit | 500 | 1 | 500 | 0 | 500 | n/a
26/3/2025 | Natural Stone | Lf | 800 | 60 | 48000 | 10000 | 58000 | Material Transport
2025-05-04 | Ballast | Tons | 16 | 1300 | 20800 | 10000 | 30800 | Material Transport
2025-05-04 | Cement | Bags | 20 | 780 | 15600 | 10000 | 25600 | Material Transport
2025-06-04 | Natural Stone | Lf | 750 | 60 | 45000 | 10000 | 55000 | Material Transport
2025-07-04 | Dust | Tons | 16 | 800 | 12800 | 10000 | 22800 | Material Transport
2025-07-04 | Dust | Tons | 16 | 800 | 12800 | 10000 | 22800 | Material Transport
2025-07-04 | Marine Board | Pcs | 10 | 3200 | 32000 | 10000 | 42000 | Material Transport
2025-07-04 | 2" Nails | Kg | 10 | 150 | 1500 | 0 | 1500 | n/a
2025-08-04 | Ballast | Tons | 16 | 1300 | 20800 | 10000 | 30800 | Material Transport
2025-09-04 | Hardcore | Trucks | 1 | 10000 | 10000 | 10000 | 20000 | Material Transport
2025-10-04 | Cutting disk (steel) | Pcs | 1 | 200 | 200 | 10000 | 10200 | Material Transport
2025-10-04 | Cutting disk (timber) | Pcs | 1 |  | 0 | 0 | 0 | n/a
2025-10-04 | Marine Board | Pcs | 5 | 3200 | 16000 | 0 | 16000 | n/a
2025-10-04 | D8 | Pcs | 40 | 620 | 24800 | 0 | 24800 | n/a
2025-10-04 | D12 | Pcs | 45 | 1320 | 59400 | 0 | 59400 | n/a
2025-10-04 | Cement | Bags | 30 | 780 | 23400 | 0 | 23400 | n/a
2025-10-04 | Hardcore | Trucks | 1 | 10000 | 10000 | 10000 | 20000 | Material Transport
2025-10-04 | Cement | Bags | 20 | 780 | 15600 | 0 | 15600 | n/a
2025-10-04 | 100 mm UPVC pipe | Pcs | 1 | 1150 | 1150 | 0 | 1150 | n/a
2025-10-04 | 75 mm UPVC pipe | Pcs | 1 | 600 | 600 | 0 | 600 | n/a
2025-10-04 | 50 mm UPVC pipe | Pcs | 1 | 450 | 450 | 0 | 450 | n/a
2025-10-04 | Hardcore | Trucks | 1 | 10000 | 10000 | 10000 | 20000 | Material Transport
2025-10-04 | Hardcore | Trucks | 0.3 | 10000 | 3000 | 10000 | 13000 | Material Transport
2025-10-04 | Diesel | Unit | 400 | 1 | 400 | 0 | 400 | n/a
2025-10-04 | Petrol | Unit | 360 | 1 | 360 | 0 | 360 | n/a
2025-10-05 | Wheelbarrow wheels | Pcs | 2 | 1600 | 3200 | 0 | 3200 | n/a
2025-11-04 | Fan belt (A66) | Pcs | 1 |  | 0 | 0 | 0 | n/a
2025-11-04 | Fan belt (A53) | Pcs | 1 |  | 0 | 0 | 0 | n/a
2025-11-04 | BRC | Rolls | 3 |  | 0 | 10000 | 10000 | Material Transport
2025-11-04 | D12 | Pcs | 6 | 1320 | 7920 | 0 | 7920 | n/a
2025-11-04 | D8 | Pcs | 6 | 620 | 3720 | 0 | 3720 | n/a
2025-11-04 | Cement | Bags | 25 | 780 | 19500 | 0 | 19500 | n/a
2025-11-04 | DPM | Rolls | 3 |  | 0 | 0 | 0 | n/a
2025-11-04 | Binding Wire | Rolls | 1 | 3200 | 3200 | 0 | 3200 | n/a
2025-12-04 | 40 mm UPVC pipe | Pcs | 5 | 400 | 2000 | 10000 | 12000 | Material Transport
2025-12-04 | 50 mm UPVC pipe | Pcs | 5 | 450 | 2250 | 0 | 2250 | n/a
2025-12-04 | 75 mm UPVC pipe | Pcs | 1 | 600 | 600 | 0 | 600 | n/a
2025-12-04 | 100 mm UPVC pipe | Pcs | 2 | 1150 | 2300 | 0 | 2300 | n/a
2025-12-04 | 4 way floor trap | Pcs | 19 | 250 | 4750 | 0 | 4750 | n/a
2025-12-04 | 100mm UPVC Bend | Pcs | 5 | 120 | 600 | 0 | 600 | n/a
2025-12-04 | 50mm UPVC Bend | Pcs | 5 | 60 | 300 | 0 | 300 | n/a
2025-12-04 | 40mm UPVC Bend | Pcs | 15 | 50 | 750 | 0 | 750 | n/a
2025-12-04 | 75mm UPVC Bend | Pcs | 10 | 100 | 1000 | 0 | 1000 | n/a
2025-12-04 | 50mm UPVC Bend(45) | Pcs | 5 | 37 | 185 | 0 | 185 | n/a
2025-12-04 | Tangit Glue (250ml) | Pcs | 4 | 500 | 2000 | 0 | 2000 | n/a
2025-12-04 | 40 mm UPVC Tee | Pcs | 5 | 60 | 300 | 0 | 300 | n/a
2025-12-04 | Hardcore | Trucks | 1 | 10000 | 10000 | 10000 | 20000 | Material Transport
14/4/2025 | Hardcore | Trucks | 1 | 10000 | 10000 | 10000 | 20000 | Material Transport
14/4/2025 | Ballast | Tons | 16 | 1300 | 20800 | 10000 | 30800 | Material Transport
14/4/2025 | 100 mm UPVC pipe | Pcs | 2 | 1150 | 2300 | 0 | 2300 | n/a
14/4/2025 | Dust | Tons | 16 | 800 | 12800 | 10000 | 22800 | Material Transport
15/4/2025 | Ballast | Tons | 16 | 1300 | 20800 | 10000 | 30800 | Material Transport
15/4/2025 | Dust | Tons | 16 | 800 | 12800 | 10000 | 22800 | Material Transport
15/4/2025 | Murram | Tons | 20 |  | 0 | 0 | 0 | n/a
15/4/2025 | Diesel | Unit | 800 | 1 | 800 | 0 | 800 | n/a
15/4/2025 | Diesel | Unit | 800 | 1 | 800 | 0 | 800 | n/a
15/4/2025 | Cement | Bags | 70 | 780 | 54600 | 10000 | 64600 | Material Transport
15/4/2025 | Dust | Tons | 16 | 800 | 12800 | 10000 | 22800 | Material Transport
15/4/2025 | DPM | Rolls | 1 |  | 0 |  | 0 | n/a
15/4/2025 | Cement | Bags | 90 | 780 | 70200 | 10000 | 80200 | Material Transport
16/4/2025 | Diesel | Unit | 500 | 1 | 500 | 0 | 500 | n/a
16/4/2025 | Petrol | Unit | 650 | 1 | 650 | 0 | 650 | n/a
16/4/2025 | Engine oil | Unit | 150 | 1 | 150 | 0 | 150 | n/a
16/4/2025 | Ballast | Tons | 16 | 1300 | 20800 | 10000 | 30800 | Material Transport
| Cement | Bags | 55 | 780 | 42900 | 10000 | 52900 | Material Transport
[5 empty] | 2196905 | 542300 | 2739205

## Sheet1
Mixer 1
2025-08-04 | Mixer 2
Vibrator 1
2025-08-04 | Vibrator 2
Poker 1
2025-08-04 | Poker 2
2025-07-04 | Trappers | 55
2025-10-04 | wheelbarrow
2025-10-04 | Mtungi | 9
14/4/2025 | Sledgehammers | 3
14/4/2025 | 210 l tanks | 6
2025-11-03 | 1000L Water tank | Pcs | 2 | 0 | 0
15/4/2025 | Wheel | Pcs | 1

## Total material received
Material | Unit | Quantity | Unit cost | Admin Cost | Total Cost
Cement | Bags | 595 | 780 | 54000 | 464100
Cement (local) | Bags | 30 | 830 | 300 | 24900
Marine Board | Pcs | 20 | 3200 |  | 64000
Hoop Iron | Rolls | 6 | 3300 |  | 19800
4" Nails | Kg | 51 | 180 |  | 9180
3" Nails | Kg | 50.5 | 180 |  | 9090
Roofing Nails | Kg | 0 | 200 |  | 0
9" Machine cut stones | Pcs | 12 | 50 |  | 600
Natural Stone | Lf | 3240 | 60 | 60000 | 194400
Roofing Sheets(10) | Pcs | 0 | 1680 |  | 0
Roofing Sheets(8) | Pcs | 40 | 1400 |  | 56000
3x2 Timber Frames | Lf | 0 | 65 |  | 0
6x1 Timber Planks | Lf | 0 | 65 |  | 0
600 x 600 Tiles | Pcs | 0 | 2000 |  | 0
Grout | Kg | 0 | 350 |  | 0
PVC Corner Strips | Pcs | 0 |  |  | 0
Reflector Jackets | Pcs | 10 | 200 |  | 2000
Hard hats | Pcs | 10 | 200 |  | 2000
D8 | Pcs | 276 | 620 |  | 171120
D10 | Pcs | 90 | 920 |  | 82800
D12 | Pcs | 211 | 1320 |  | 278520
D16 | Pcs | 135 | 2350 |  | 317250
Binding Wire | Kg | 7 | 3200 |  | 22400
Hacksaw Blade | Pcs | 18 | 100 | 0 | 1800
A3 Safety signage | Pcs | 2 | 3500 | 2000 | 7000
PPR(25mm) | Metres | 300 |  |  | 0
Ballast | Tons | 181 | 1300 | 88800 | 235300
Dust | Tons | 181 | 800 | 81400 | 144800
150mm UPVC Bend | Pcs | 1 | 150 |  | 150
First aid box | Pcs | 1 |  |  | 0
Grease | Kg | 1.5 | 500 | 0 | 750
Petrol | Unit | 3510 | 1 | 0 | 3510
Diesel | Unit | 5850 | 1 | 0 | 5850
BRC | Rolls | 5 |  | 0 | 0
2" Nails | Kg | 10 | 150 | 0 | 1500
Hardcore | Trucks | 5.3 | 10000 | 60000 | 53000
Cutting disk (steel) | Pcs | 1 | 200 | 0 | 200
Cutting disk (timber) | Pcs | 1 |  | 0 | 0
Fan belt (A66) | Pcs | 1 |  |  | 0
Fan belt (A53) | Pcs | 1 |  |  | 0
DPM | Rolls | 4 |  |  | 0
4 way floor trap | Pcs | 19 | 250 |  | 4750
40 mm UPVC pipe | Pcs | 5 | 400 |  | 2000
50 mm UPVC pipe | Pcs | 6 | 450 |  | 2700
75 mm UPVC pipe | Pcs | 2 | 600 |  | 1200
100 mm UPVC pipe | Pcs | 5 | 1150 |  | 5750
100mm UPVC Bend | Pcs | 5 | 120 |  | 600
50mm UPVC Bend | Pcs | 5 | 60 |  | 300
40mm UPVC Bend | Pcs | 15 | 50 |  | 750
75mm UPVC Bend | Pcs | 10 | 100 |  | 1000
50mm UPVC Bend(45) | Pcs | 5 | 37 |  | 185
Tangit Glue (250ml) | Pcs | 4 | 500 |  | 2000
40 mm UPVC Tee | Pcs | 5 | 60 |  | 300
Wheelbarrow wheels | Pcs | 2 | 1600 |  | 3200
Waterproofing cement | Kg | 3 |  |  | 0
Engine oil | Unit | 150 | 1 |  | 150
TOTAL |  |  |  |  | 2196905
0

## Material spent 1
Date | Material | Units | Quantity | Purpose | Material quantity | rate | labor cost | rate
26/2/2025 | Cement | Bags | 14 | Blinding | 0.16 | m2 | 91 | m2
26/2/2025 | D16 | Metres | 96 | Column reinforcement | 19 | hr | 11 | kg
26/2/2025 | D12 | Metres | 24 | Column reinforcement | 2.63 | hr | 11 | kg
26/2/2025 | D10 | Metres | 240 | Strip footing reinforcement | 18 | hr | 11 | kg
26/2/2025 | D8 | Metres | 96 | Column reinforcement | 4 | hr | 11 | kg
26/2/2025 | D8 | Metres | 28 | Strip footing reinforcement | 1 | hr | 11 | kg
2025-04-03 | D10 | Metres | 240 | Strip footing reinforcement | 16 | hr | 15.5 | kg
2025-04-03 | D8 | Metres | 28 | Strip footing reinforcement | 10 | hr | 15.5 | kg
2025-04-03 | Cement | Bags | 31 | Foundation Concrete | 6.88 | m3 | 1020.86 | m3
2025-06-03 | D8 | Metres | 84 | Column reinforcement | 21.25 | hr | 19 | kg
2025-06-03 | Cement | Bags | 7.5 | Blinding | 0.216 | m2 | 265.9 | m2
2025-07-03 | D8 | Metres | 84 | Column reinforcement | 18 | hr | 22 | kg
2025-08-03 | Cement | Bags | 22 | Foundation Concrete | 6.89 | m3 | 2725.56 | m3
2025-09-03 | Roofing sheets (8) | Metres | 19.2 | Hoarding | 1.25 | m | 78 | m
2025-11-03 | Cement | Bags | 26.5 | Foundation Concrete | 4.16 | m3 | 1603.7 | m3
2025-12-03 | Cement | Bags | 34.5 | Foundation Concrete | 4.38 | m3 | 1295 | m3
13/3/2025 | Cement | Bags | 25 | Foundation Concrete | 4.49 | m3 | 1833.9 | m3
14/3/2025 | 3x2 | Metres | 16.8 | Kickers | 4.2 | hr | 89 | m
14/3/2025 | Marine board | Square metres | 2.52 | Column Formwork | 0.315 | hr | 297.6 | m2
14/3/2025 | Cement | Bags | 28 | Foundation Concrete | 3.3 | m3 | 1144.95 | m3
15/3/2025 | Cement | Bags | 12 | Foundation Concrete | 4.27 | m3 | 1095.085 | m3
17/3/2025 | Cement | Bags | 5 | Column Concrete | 5.02 | m3 | 2792.67 | m3
18/3/2025 | Cement | Bags | 9 | Foundation walling | 0.075 | lm | 50 | lm
18/3/2025 | Marine board | Square metres | 0.48 | Column Formwork | 0.06 | hr | 3125 | m2
18/3/2025 | Marine board | Square metres | 0.96 | Column Formwork (Mounting) | 0.12 | hr | 3593 | m2
18/3/2025 | Cement | Bags | 2.5 | Column Concrete | 3.37 | m3 | 4184.67 | m3
19/3/2025 | Cement | Bags | 9 | Foundation walling | 0.116 | lm | 77 | lm
19/3/2025 | D8 | Metres | 120 | Ground beam reinforcement | 15 | hr | 42.18 | kg
19/3/2025 | Marine board | Square metres | 0.48 | Column Formwork (Mounting) | 0.6 | hr | 3750 | m2
22/3/2025 | Cement | Bags | 11 | Foundation walling | 0.079 | lm | 68.47 | lm
24/3/2025 | Cement | Bags | 7 | Foundation walling | 0.104 | lm | 77 | lm
26/3/2025 | Cement | Bags | 6 | Foundation Concrete | 3.17 | m3 | 1111 | m3
26/3/2025 | D12 | Metres | 180 | Ground beam reinforcement | 20 | hr | 12.5 | kg
26/3/2025 | D8 | Metres | 205.2 | Ground beam reinforcement | 10 | hr | 24.69 | kg

## Total material spent
Category | Material used | quantity | units | Mean Labor cost | rate | Mean material quantity | rate
Blinding | Cement | 21.5 | Bags | 178.45 | m2 | 0.188 | m2
Column reinforcement | D8 | 264 | Metres | 14.8 | kg | 12.976 | hr
Column reinforcement | D12 | 24 | Metres | 14.8 | kg | 12.976 | hr
Column reinforcement | D16 | 96 | Metres | 14.8 | kg | 12.976 | hr
Strip footing reinforcement | D8 | 56 | Metres | 13.25 | kg | 11.25 | hr
Strip footing reinforcement | D10 | 480 | Metres | 13.25 | kg | 11.25 | hr
Foundation Concrete | Cement | 185 | Bags | 1478.7569 | m3 | 4.6925 | m3
Hoarding | Roofing sheets (8) | 19.2 | Metres | 78 | lm | 1.25 | lm
Kickers | 3x2 | 16.8 | Metres | 89 | lm | 4.2 | lm
Column Formwork | Marine board | 3 | Square metres | 1711.3 | sm | 0.1875 | hr
Column Formwork (Mounting) | Marine board | 1.44 | Square metres | 3671.5 | sm | 0.36 | hr
Column Concrete | Cement | 7.5 | Bags | 3488.67 | m3 | 4.195 | m3
Foundation walling | Cement | 36 |  | 68.1175 | lm | 0.0935 | lm
Ground beam reinforcement | D8 | 325.2 |  | 26.4567 | kg | 15 | hr

## Cumulatively tracked material
47.4074
42.1875